*Table 1. Timelines for preparing the projections*

|  |  |  |
| --- | --- | --- |
| **Main players** | **Activities** | **Timing** |
| GHG projection experts | Data collection including new data agreements:   * Collecting new raw data * Revision of methods * Updating Parameters | 10 months and 3 months prior to submission |
| PAMs experts | Projection Compilation:   * Incorporating PAMs * Assessment of projection estimates * Compiling domestic totals * Compiling PAMs | 5 months and 2 months prior to submission |
| GHG projection experts & PAMs experts | Submission checks: by 15 March every two years:   * Filling data into the reporting formats; * Description of the methods, assumptions and data sources; | 1-2 month prior to submission (by January-February) |